## Slide 1
ACCOUNT + PROJECT MANAGEMENT PORTFOLIO
Delivering an international AGM travel program through disruption
MRS Oil Annual General Meeting (AGM) travel program
Nairobi, Kenya | Feb 2020–Mar 2021
180
travelers
₦165m
revised budget
Agnes Iwaye | Account Manager / Project Lead

## Slide 2
A routine annual trip became a high-risk transformation project
02
ORIGINAL BRIEF
Coordinate a seamless AGM trip
Flights, accommodation, conference space, local transport, leisure activities and executive-level traveler support for a large employee group.
Delivery scale
180 travelers • 5 days / 4 nights • multiple Nigerian and Kenyan suppliers
DISRUPTION
COVID changed the constraints
Evolving entry, testing, health-documentation, capacity, insurance and supplier requirements increased cost and reduced schedule certainty.
Management response
Rebaseline scope, budget, risk controls, vendor terms, communications and emergency readiness.

## Slide 3
I coordinated one operating model across nine stakeholder groups
03
CLIENT
MRS Oil sponsor
HR / traveler coordinators
Executives and employees
INTERNAL
Travel consultants
Finance and credit
Finchglow Holidays
Account leadership
KENYA DELIVERY
Hotel and conference venue
Ground transport
Destination activities
Local coordination
ASSURANCE
Medical partner / doctor
Insurance support
Risk and escalation contacts
Backup suppliers
My role: translate client needs into one schedule, one budget, one risk view and one daily execution plan

## Slide 4
A fourteen-month roadmap protected momentum through uncertainty
04
FEB
MAR
APR
MAY
JUN
JUL
AUG
SEP
OCT
NOV
DEC
JAN
FEB
MAR
Charter + destination
COVID assessment
Sourcing + itinerary
Contract + finance
Rebaseline + risk
Traveler readiness
Execute + close
2020
2021

## Slide 5
Six integrated workstreams converted the itinerary into an executable program
05
FLIGHTS
Group seat blocks
Flexible fare rules
Manifest and ticket control
HOTEL
90 twin rooms
Rooming list governance
Overflow capacity
MOVEMENT
Airport transfers
Daily buses and dispatch
Standby vehicle
AGM + ACTIVITIES
Conference venue and AV
Timed group activities
Weather alternatives
HEALTH + SAFETY
Entry/test documentation
Standby doctor
Referral and evacuation path
TRAVELER CHANGE
Briefings and packs
Help desk and coordinators
Exception tracking
Control mechanism: integrated master schedule • daily readiness dashboard • vendor tracker • RAID log • command-center escalation

## Slide 6
The budget was rebaselined by 25%—then closed below the new ceiling
06
₦ MILLIONS
Original baseline
₦132m
Revised approval
₦165m
Modeled actual
₦160.5m
₦33.0m rebaseline
Flights, capacity, medical support, flexible terms and contingency
₦4.5m below revised budget
2.7% saving at modeled closeout

## Slide 7
Credit exposure was controlled through staged commitments
07
1 BASELINE
Consolidate flights, rooms, venue, movements, activities and assurance costs.
2 NEGOTIATE
Secure flexible terms, attrition clauses, cancellation windows and backup capacity.
3 STRUCTURE
Align client payments, vendor deposits and Finchglow credit approvals by milestone.
4 CONTROL
Run weekly exposure, deposit, variance and exception reviews until closeout.
Commercial controls
Named owner and service-level commitment
Deposit due date and approval gate
Backup supplier or alternative itinerary
Invoice validation before final settlement

## Slide 8
High-impact risks had named controls, triggers and backups
08
Risk | Rating | Primary response
Entry or testing rule change | High | Monitor rules; traveler checklist; decision gate
Flight cancellation | High | Flexible fares; alternative routing; escalation contact
Traveler illness | High | Standby doctor; referral hospital; insurance and evacuation
Credit exposure | High | Staged payments; weekly exposure review; approval gates
Transport supplier failure | Medium | Backup fleet; dispatch channel; standby vehicle
Hotel / venue capacity | Medium | Overflow rooms; alternate ballroom; flexible clauses
Risk-review questions
What changed?
Which travelers or suppliers are affected?
What decision is due—and by when?
Which contingency is ready to activate?

## Slide 9
A command-center model shortened the path from incident to decision
09
1 DETECT
Traveler coordinator or vendor raises an alert
Time and location logged
2 TRIAGE
Account lead validates impact
Medical/logistics lead engaged
3 DECIDE
Escalate to client sponsor
Activate approved contingency
4 RECOVER
Rebook, reroute or treat
Reconcile traveler and document closure
Prepared capabilities
Standby doctor • referral hospital • insurance escalation • backup fleet • alternate routing • emergency contacts • traveler reconciliation

## Slide 10
The March 2021 program closed with full traveler reconciliation
10
180
travelers supported
100%
manifest reconciliation
96%
on-time movements
92%
traveler satisfaction
Outcome area | Illustrative closeout evidence | Result
Safety | No major safety incidents | Met
Financial | ₦160.5m actual vs ₦165.0m revised | ₦4.5m below
Readiness | All 180 travelers cleared by departure | 100%
Governance | Vendor, risk and closeout records completed | Closed