## Portfolio Summary
MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya
MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya | MRS Oil Annual General Meeting Travel Program — Nairobi, Kenya
Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights | Project period: Feb 2020–Mar 2021 ¦ Role: Account Manager / Project Lead ¦ 180 travelers ¦ 5 days / 4 nights
Business context | Finchglow Travels coordinated an international annual general meeting travel program for MRS Oil employees and executives. |  | SUCCESS CRITERIA | SUCCESS CRITERIA | SUCCESS CRITERIA | SUCCESS CRITERIA | SUCCESS CRITERIA
Project objective | Plan and execute end-to-end travel, accommodation, conference, ground transport, leisure and traveler-support services in Nairobi. |  | 1. All travelers ticketed, documented and briefed before departure
Complexity | 180 travelers; cross-functional delivery; multiple Kenyan vendors; credit constraints; evolving COVID-19 entry, testing, capacity and safety requirements. |  | 2. Conference, hotel, transport and leisure vendors contracted and confirmed
My responsibilities | Requirements gathering, stakeholder coordination, schedule, vendor management, budget control, credit negotiation, risk planning, traveler communications and execution oversight. |  | 3. Revised spending maintained within the approved ₦165 million ceiling
Original budget | ₦132.0 million — illustrative pre-COVID baseline. |  | 4. Health, medical, evacuation and supplier-failure contingencies activated
Revised budget | ₦165.0 million after a 25% COVID-era rebaseline. |  | 5. Daily movements delivered safely with rapid incident escalation
Actual spend | ₦160.5 million — ₦4.5 million below revised budget. |  | 6. Program closed with reconciled invoices, feedback and lessons learned
Execution | Five-day/four-night Nairobi program delivered in March 2021 with conference sessions, local movements, group activities and medical standby.
Illustrative outcome | 180 travelers supported; 100% manifest reconciliation; 96% on-time movements; 92% satisfaction; no major safety incidents.

## Project Timeline
Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline
Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline | Fourteen-Month Project Timeline & COVID-19 Rebaseline
Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements. | Blue bars show the planning window. The December 2020 rebaseline incorporated new health, supplier and contingency requirements.
Workstream | Activity | Start | Finish | Owner | Deliverable | Feb-20 | Mar-20 | Apr-20 | May-20 | Jun-20 | Jul-20 | Aug-20 | Sep-20 | Oct-20 | Nov-20 | Dec-20 | Jan-21 | Feb-21 | Mar-21 | Status
Initiation | Prior-trip review, charter and requirements | 2020-02-03 | 2020-02-28 | Account Manager | Approved charter | 1 | [13 empty] | Complete
Planning | Destination options and feasibility | 2020-02-17 | 2020-03-20 | Account Manager | Nairobi recommendation | 1 | 1 | [12 empty] | Complete
Disruption | COVID impact assessment and planning pause | 2020-03-16 | 2020-04-30 | Project Team | Impact assessment |  | 1 | 1 | [11 empty] | Complete
Sourcing | Flights, hotel and venue RFP | 2020-05-04 | 2020-06-26 | Travel/Holidays | Vendor options |  |  |  | 1 | 1 | [9 empty] | Complete
Design | Draft itinerary and event program | 2020-06-15 | 2020-08-07 | Account Manager | Integrated itinerary |  |  |  |  | 1 | 1 | 1 | [7 empty] | Complete
Contracting | Hotel, transport and venue contracting | 2020-08-03 | 2020-10-16 | Procurement/Legal | Signed agreements | [6 empty] | 1 | 1 | 1 | [5 empty] | Complete
Finance | Credit structure and deposit schedule | 2020-09-01 | 2020-11-13 | Finance/Account Manager | Funding plan | [7 empty] | 1 | 1 | 1 |  |  |  |  | Complete
Rebaseline | COVID requirements, budget and schedule reset | 2020-11-02 | 2020-12-18 | Account Manager | Approved rebaseline | [9 empty] | 1 | 1 |  |  |  | Complete
Risk | Medical, evacuation and contingency plan | 2020-12-01 | 2021-01-29 | Risk/Medical | Emergency plan | [10 empty] | 1 | 1 |  |  | Complete
Readiness | Traveler data, documents and health readiness | 2021-01-04 | 2021-02-26 | Travel Team | Cleared traveler list | [11 empty] | 1 | 1 |  | Complete
Comms | Briefings, itinerary packs and help desk | 2021-02-01 | 2021-03-05 | Account Manager | Traveler packs | [12 empty] | 1 | 1 | Complete
Finalization | Vendor confirmations and command-center test | 2021-02-15 | 2021-03-05 | Project Team | Go-live checklist | [12 empty] | 1 | 1 | Complete
Execution | Nairobi AGM travel program | 2021-03-08 | 2021-03-12 | All Leads | Successful program | [13 empty] | 1 | Complete
Closeout | Invoice reconciliation and lessons learned | 2021-03-15 | 2021-03-31 | Account Manager/Finance | Closeout report | [13 empty] | 1 | Complete
[6 empty] | 43862 | 43891 | 43922 | 43952 | 43983 | 44013 | 44044 | 44075 | 44105 | 44136 | 44166 | 44197 | 44228 | 44256
[6 empty] | 43890 | 43921 | 43951 | 43982 | 44012 | 44043 | 44074 | 44104 | 44135 | 44165 | 44196 | 44227 | 44255 | 44286

## Budget Control
Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions
Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions | Budget Control & COVID-19 Rebaseline — ₦ Millions
Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget. | All amounts are illustrative. Positive revised variance means actual spend was below the revised budget.
Cost category | Original budget | Revised budget | Actual spend | Rebaseline increase | Variance to revised | Actual / revised | Comment
International flights | 56 | 66 | 67.8 | 10 | -1.8 | 102.7% | Higher fares and schedule flexibility
Hotel accommodation | 35 | 41.25 | 39.8 | 6.25 | 1.45 | 96.48% | Flexible room block and health protocols
Ground transportation | 10 | 13.2 | 12.7 | 3.2 | 0.5 | 96.21% | Additional vehicles and capacity controls
Conference venue & AV | 9 | 11.55 | 11.2 | 2.55 | 0.35 | 96.97% | Spacing, equipment and revised event setup
Group activities | 8 | 9.9 | 9.5 | 1.9 | 0.4 | 95.96% | Rescheduled and lower-density activities
Health & safety | 2 | 8.25 | 8.8 | 6.25 | -0.55 | 106.7% | Testing, PPE, standby doctor and medical support
Insurance, visa & admin | 4 | 4.95 | 4.8 | 0.95 | 0.15 | 96.97% | Expanded travel support and documentation
Contingency reserve | 8 | 9.9 | 5.9 | 1.9 | 4 | 59.6% | Risk reserve partially consumed
TOTAL | 132 | 165 | 160.5 | 33 | 4.5 | 97.27% | Modeled closeout

## Vendor Tracker
Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker
Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker | Vendor & Contract Tracker
Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya. | Track critical commercial, operational and contingency commitments across Nigeria and Kenya.
Package | Vendor type | Location | Contract value (₦m) | Deposit % | Deposit (₦m) | Status | SLA / commitment | Backup plan | Owner
Flights | Airline/GDS | Nigeria–Kenya | 66 | 35% | 23.1 | Confirmed | Group seats; rebooking escalation | Alternative routing/airline | Travel Lead
Accommodation | Hotel | Nairobi | 41.25 | 30% | 12.375 | Confirmed | 90 twin rooms; flexible rooming list | Overflow hotel block | Holidays Lead
Ground transport | Transport operator | Nairobi | 13.2 | 25% | 3.3 | Confirmed | Buses, airport transfers, standby vehicle | Secondary fleet provider | Local Logistics
Conference | Venue & AV | Nairobi | 11.55 | 40% | 4.62 | Confirmed | Conference hall, AV, spacing setup | Hotel ballroom | Events Lead
Activities | DMC / attractions | Kenya | 9.9 | 30% | 2.97 | Confirmed | Timed group activities and guides | Indoor alternative itinerary | Holidays Lead
Medical | Clinic / doctor | Nairobi | 8.25 | 50% | 4.125 | Confirmed | Standby doctor and referral pathway | Partner hospital escalation | Risk Lead
Insurance/admin | Insurer & support | Nigeria/Kenya | 4.95 | 60% | 2.97 | Confirmed | Traveler coverage and document support | Escalate to broker | Account Manager

## RAID Log
RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk
RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk | RAID Log — Travel, Health, Financial & Supplier Risk
Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7. | Risk score = probability × impact. High: 15–25; Medium: 8–14; Low: 1–7.
ID | Type | Description | Probability | Impact | Score | Rating | Response / control | Owner | Trigger | Status | Review date
R-01 | Risk | Border, entry or testing requirements change | 4 | 5 | 20 | High | Monitor rules; maintain document checklist; define rerouting/postponement decision gate | Account Manager | Policy change | Mitigated | 2021-03-01
R-02 | Risk | Flight cancellation or major schedule disruption | 3 | 5 | 15 | High | Flexible fares; backup routing; airline escalation contact; traveler regrouping plan | Travel Lead | Schedule change | Mitigated | 2021-03-01
R-03 | Risk | Traveler illness or medical emergency | 3 | 5 | 15 | High | Standby doctor; referral hospital; insurance; isolation and evacuation protocol | Risk Lead | Reported symptoms | Mitigated | 2021-03-05
R-04 | Risk | Local transport supplier failure | 3 | 4 | 12 | Medium | Backup fleet; daily vehicle checks; dispatch command channel | Logistics Lead | Vehicle no-show | Mitigated | 2021-03-05
R-05 | Risk | Credit exposure exceeds internal limit | 4 | 4 | 16 | High | Staged client payments; deposit calendar; weekly exposure review; approval gates | Finance Lead | Exposure > limit | Closed | 2021-02-19
R-06 | Risk | Hotel or venue capacity constraints | 3 | 4 | 12 | Medium | Flexible room block; overflow hotel; alternative ballroom; attrition clauses | Holidays Lead | Capacity reduction | Mitigated | 2021-02-26
R-07 | Risk | Budget inflation or FX movement | 4 | 4 | 16 | High | Budget rebaseline; negotiated rates; contingency reserve; variance reporting | Account Manager | Variance > 5% | Closed | 2021-03-19
A-01 | Assumption | 180 travelers submit accurate data by cutoff | 3 | 3 | 9 | Medium | Named coordinators; exception list; weekly readiness dashboard | MRS Oil HR | Readiness < 90% | Validated | 2021-02-26

## RACI
Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI
Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI | Project Governance RACI
Activity | Account Manager | MRS Oil Sponsor | Travel Consultants | Finance | Holidays Team | Kenya Vendors | Risk/Medical | Traveler Coordinators
Charter and requirements | R/A | A | C | C | C | I | C | C
Destination and itinerary | R/A | C | R | I | R | C | C | I
Flight booking | A | I | R | C | I | I | C | C
Credit and payment plan | R | C | C | A/R | C | I | I | I
Hotel and venue sourcing | A | C | I | C | R | R | C | I
Ground transport | A | I | I | C | R | R | C | I
COVID/health requirements | A | C | C | I | C | C | R | C
Traveler documentation | A | C | R | I | I | I | C | R
Emergency response plan | A | I | C | I | C | C | R | I
On-site execution | A/R | I | R | I | R | R | R | C
Closeout and reconciliation | R/A | C | C | R | C | C | C | I

## Traveler Readiness
Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only
Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only | Traveler Readiness Dashboard — Aggregate Data Only
Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180. | Illustrative aggregate tracking avoids exposing personal traveler data. Readiness rate = fully cleared travelers ÷ 180.
Checkpoint | Total travelers | Passport verified | Ticketed | Hotel assigned | Health documents | Briefing complete | Fully cleared | Readiness rate | Open exceptions
8 weeks before | 180 | 115 | 90 | 70 | 40 | 0 | 28 | 15.56% | 152
6 weeks before | 180 | 145 | 130 | 110 | 85 | 20 | 72 | 40% | 108
4 weeks before | 180 | 165 | 158 | 150 | 135 | 90 | 126 | 70% | 54
2 weeks before | 180 | 176 | 174 | 172 | 168 | 154 | 162 | 90% | 18
1 week before | 180 | 179 | 179 | 178 | 176 | 175 | 174 | 96.67% | 6
Departure day | 180 | 180 | 180 | 180 | 180 | 180 | 180 | 100% | 0

## Executive Dashboard
Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program
Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program | Executive Dashboard — MRS Oil Nairobi AGM Travel Program
Travelers | Travelers | Revised budget | Revised budget | Actual spend | Actual spend | Budget saving | Budget saving | On-time movements | On-time movements | Satisfaction | Satisfaction
180 |  | 165 |  | 160.5 |  | 4.5 |  | 96% |  | 92%
Metric | Target | Result | Status |  | TRAVELER CLEARANCE TRAJECTORY | TRAVELER CLEARANCE TRAJECTORY | TRAVELER CLEARANCE TRAJECTORY | TRAVELER CLEARANCE TRAJECTORY | TRAVELER CLEARANCE TRAJECTORY | TRAVELER CLEARANCE TRAJECTORY | TRAVELER CLEARANCE TRAJECTORY
Fully cleared before departure | 180 | 180 | Met |  | 8 weeks | 28 | 15.6% | 6 weeks | 72 | 40%
Manifest reconciliation | 100% | 100% | Met |  | 4 weeks | 126 | 70% | 2 weeks | 162 | 90%
On-time movements | 95% | 96% | Met |  | 1 week | 174 | 96.7% | Departure | 180 | 100%
Traveler satisfaction | 90% | 92% | Met |  | Metric | Cleared | Rate | Metric | Cleared | Rate
Major safety incidents | 0% | 0% | Met |  | Readiness gain |  |  | Open exceptions
Spend within revised budget | 165 | 160.5 | Met |  | Start to departure | 152 |  | Departure day | 0 | 0
Closeout summary | Closeout summary | Closeout summary | Closeout summary
The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan.
The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan.
The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan.
The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan. | The program was rebaselined for pandemic-era requirements, delivered within the revised budget, and supported all 180 travelers through a structured command center, supplier controls and medical contingency plan.
Checkpoint | Fully cleared
8 weeks before | 28
6 weeks before | 72
4 weeks before | 126
2 weeks before | 162
1 week before | 174
Departure day | 180